## KT
KT Plan
# | Topics | Efforts (Hrs) | Start Date | End Date | Status | Remarks
1 | GIT Project Creation | 1 | 2022-07-01 | 2022-07-01 | Finished
2 | GIT Commands | 3 | 2022-10-01 | 2022-10-01 | Finished
3 | CM Process | 2 | 2022-11-01 | 2022-12-01 | Finished
4 | GIT Tag Creation | 1 | 13/1/2022 | 13/1/2022 | Finished
5 | SVN to GIT file transfer | 2 | 13/1/2022 | 13/1/2022 | Finished
6 | SDPM Overview | 2 | 17/1/2022 | 17/1/2022 | Finished
7 | UniPhase screen | 1 | 18/1/2022 | 18/1/2022 | Finished
8 | Access Management | 2 | 2022-07-01 | 2022-07-01 | Finished
9 | SVN Overview | 1 | 19/1/2022 | 19/1/2022 | Finished
10 | PTC Integrity tool Overview | 2 | 20/1/2022 | 20/1/2022 | In Progress
11 | Release activity and documentation | 2 | 21/1/2022 | 21/1/2022 | Finished
12 | License tracking | 2 | 2022-08-02 | 2022-09-02 | Finished
13 | HW Inventory tracking | 3 | 15/2/2022 | 16/2/2022 | Finished
14 | Katapult Config | 2 | 22/2/2022 | 22/2/2022 | Finished
15 | Zf Inverter Project Setup | 4 | 2022-03-03 | 2022-03-03 | Finished
16 | Manuals | 2 | 24/1/2022 | 24/1/2022 | Finished
| Total Effort | 32 | HRS
Dates are tentative, may be changed based on availability/ time constraints.