## Sheet1
Category | Frequency | Milestone Model1-M1 | Deliverables/ Phase | Tool | Tool detail | Implemented | KPI | Metric | Formula | Measurable Entity | UOM | Data Type | Metric Classification | Example
DELIVERY | Quarterly |  | CSAT |  |  |  | Customer Satisfaction | CSAT Rating | Rating Scale 1 to 5 | Process (Project) | Number | Continuous | Larger the Better | NA
DELIVERY | Milestone Delivery | Yes | Milestone | KAP |  |  | On Time Delivery | On Time Delivery % | (No. of On Time Deliveries/Total no. of deliveries made)*100 | Process (Project) | % | Ratio | Larger the Better | No. of On Time Deliveries = 8 Total No. of Deliveries = 10 On Time Delivery Percentage = (8 / 10) * 100 = 80%
DELIVERY | Milestone Delivery | Yes | release | KAP |  |  | Schedule Variance | Schedule Variance - Phase | (Actual calendar days for phase – Planned calendar days for Phase) / Planned calendar days for phase * 100 | Process (Phase) | % | Ratio | Smaller the Better | Planned Duration = 50 Calendar Days Actual Duration = 52 Calendar Days Schedule Variance = (52 - 50) / 50 * 100 = 4%
QUALITY | Monthly | Yes | Code | Katapult (CPD) | CPD | Yes | Code Quality | % Duplication | Duplicate blocks of code/ Total lines of code | Product | % | Ratio | Lower the better
QUALITY | Monthly | Yes | Code | Katapult (CLOC) | CLOC | Yes | Code Quality | Code Comments % | Lines of code as comments/ Total lines of code | Product | % | Ratio | NA | Between 20% and 50%
QUALITY | Monthly | Yes | Code | Katapult | Tessy | Yes | Code Quality | Code Coverage (Software / Integration Test) | Number of lines of code Tested/Total lines of code executed | Product | % | Ratio | Larger the Better
QUALITY | Monthly | Yes | Code | Katapult | Tessy | Yes | Code Quality | Code Coverage (Unit Test) | Number of lines of code Tested/Total lines of code executed | Product | % | Ratio | Larger the Better
QUALITY | Monthly | Yes | Code | Katapult | Polyspace (R2019b) | Yes | Code Quality | Code Violation (Dynamic code check e.g. Polyspace) | Refer Katapult Guidelines | Product | Number | Discrete | Lower the better
QUALITY | Monthly | Yes | Code | Katapult | (QAC-9.3 8.1.1R MISRA) | Yes | Code Quality | Code Violation (Static code check) | Refer Katapult Guidelines | Product | Number | Discrete | Lower the better
QUALITY | Monthly | Yes | Code | Katapult | (QAC-9.3 8.1.1R MISRA) | Yes | Code Quality | Compiler Warnings | Number of compiler warnings | Product | Number | Discrete | Lower the better
QUALITY | Monthly | Yes | Code | Katapult | (Lizard) | Yes | Code Quality | Complexity of Most Complex Function | Refer Katapult Guidelines | Product | Number | Discrete | Lower the better
QUALITY | Monthly | Yes | Code | Katapult | ( Lizard) | Yes | Code Quality | McCabe's Cyclomatic Complexity | Edges - Nodes + 2 X Connections | Product | Number | Continuous | Moderate the Best | NA
QUALITY | Monthly | Yes | Unit Testing | Katapult | Excel | Yes | Code Quality | Pass Percentage (Software / Integration Test) | Number of Test Cases Passed/ Number of Total Test Cases | Product | % | Ratio | Larger the Better
QUALITY | Monthly | Yes | Unit Testing | Katapult | Excel | Yes | Code Quality | Pass Percentage (Unit Test) | Number of Unit Test Cases Passed/ Number of Unit Total Test Cases Executed | Product | % | Ratio | Larger the Better
QUALITY | Milestone Delivery | Yes | Code | Katapult | DOOR/ excel | Yes | Code Quality | Requirements Implementation Coverage | (No. of Requirements Implemented / Total No. of Requirements) * 100 | Process (Project) | % | Ratio | Larger the Better
QUALITY | Milestone Delivery | Yes | release | Redmine |  |  | Defect Density | Delivered Defect Density - Project | No. of Discontinuities Escaped, Reported By Customer / Total Size of the Project in KSLOC | Process (Project) | DE/SLOC | Continuous | Smaller the Better | DEs reported By Customer = 3 Total Size of Project = 2080 SLOC = 2.1 KSLOC Delivered Defect Density - Project = (3/2.1) = 1.4
QUALITY | Milestone Delivery | No | release | Redmine |  |  | Defect Density | Escaped Defect Density - Phase | No. of Discontinuities Escaped In Uniphase/Total Size of the Phase in KSLOC | Process (Phase) | DE/SLOC | Continuous | Smaller the Better | DEs Reported Internally = 2 Total Size of Phase = 2080 SLOC = 2.1 KSLOC Delivered Defect Density - Phase = (3/2.1) = 0.9
QUALITY | Milestone Delivery | Yes | release | Redmine |  |  | Defect Rate | Delivered Defect Rate - Project | No. of Discontinuities Escaped reported By Customer / Total Effort of the Project | Process (Project) | DE/PM | Continuous | Smaller the Better | DEs reported By Customer = 3 Total Effort of Project = 5.4 PM Delivered Defect Rate - Project = (3/5.4) = 0.5
QUALITY | Milestone Delivery | No | SW Architecture | Excel |  |  | Design Quality | Coupling (X,Y) ( AUTOSAR Authorizing tool or excel based ) | i+ (n/n+1), where n=number of interactions between X & Y | Product | Number | Continuous | Moderate the Best | NA
QUALITY | Milestone Delivery | No | SW Architecture | Excel |  |  | Design Quality | Modularity Index | Number of Interactions among modules/Total Number of Modules | Product | Number | Continuous | Moderate the Best | NA
QUALITY | Milestone Delivery | Yes | release | Unipro |  |  | First Time Right | FTR% based on External & Internal RE | 100 - (Rework Effort to fix findings from Review, Screen, Katapult, Testing, Customer / Total Effort x 100) | Process (Project) | % | Ratio | Larger the Better
QUALITY | Milestone Delivery | No | product | PLS UDE Debugger |  |  | Product Performance | FOC task Execution time | Time taken to execute the FOC task | Product | micro-seconds | Continuous | Lower the better | Ideally task execution should complete in <60uS. Timing Architect tool can be used or pin toggling mechanism or debugger with trace option can be used to measure
QUALITY | Milestone Delivery | yes | product | PLS UDE Debugger | Oscilloscope | V&V | Product Performance | OS task Nominal Execution time | Time taken to execute the 1mS task (Using Code Instrumentation or oscilloscope) | Product | milli-seconds | Continuous | Lower the better | Ideally task execution should complete in <700uS. Timing Architect tool can be used or pin toggling mechanism or debugger with trace option can be used to measure
QUALITY | Milestone Delivery | Yes | product | PLS UDE Debugger |  | Integration | Product Performance | Starte Up time (First frame transmission time) | Time from the system start to first frame transmission (mS) | Product | milli-seconds | Continuous | Lower the better | Recommended value from KPIT Autosar practice 100 to 150ms. Can be measured by toggling a pin after first frame is transmitted. Oscilloscope can be used to measure. If ECU is already running, then time between last frame successful transmission to first frame can also be measured (Excluding shutdown time). Timing Architect tool can be used to measure as well
QUALITY | Milestone Delivery | No | product | PLS UDE Debugger |  |  | Product Performance | NVM read all during Start up time (Read all time) | Time taken to read back from the memory (mS) | Product | milli-seconds | Continuous | Lower the better | Recommended value from KPIT Autosar practice <50ms. Can be measured by using a 1mS timer or by toggling a pin before read all function and after read all completion. Timing Architect tool can be used to measure as well
QUALITY | Milestone Delivery | Yes | product | PLS UDE Debugger |  | Integration | Product Performance | CPU Load (Debugger or XCP) | 1-(Number of processes running in the memory*Average % of time processes are waiting in I/O) | Product | % | Ratio | Lower the better | Recommended range from KPIT Autosar practice 70-75%. Can be measured by pin toggling mechanism or Timing Architect tool
QUALITY | Milestone Delivery | Yes | product | Map File |  | Integration | Product Performance | RAM (Offline from MAP file ) | In Kilo Bytes | Product | Kilo Bytes | Number | Moderate the Best | NA
QUALITY | Milestone Delivery | Yes | product | Map File |  | Integration | Product Performance | RAM Utilization | [Total Memory - (Free + Buffers + Cached)]/ Total Memory | Product | % | Ratio | Lower the better | Recommended value from KPIT Autosar practice <60%. Autosar Stack utilization measurement can be done using the Autosar OS feature. RAM utilization can be measured by using MAP file
QUALITY | Milestone Delivery | Yes | product | Map File |  | Integration | Product Performance | ROM | In Kilo Bytes | Product | Kilo Bytes | Number | Moderate the Best | NA
QUALITY | Milestone Delivery | Yes | product | Map File |  | Integration | Product Performance | ROM Utilization | [Total Memory - (Free + Buffers + Cached)]/ Total Memory | Product | % | Ratio | Lower the better | Recommended value from KPIT Autosar practice <60%. ROM utilization can be measured using MAP file
QUALITY | Milestone Delivery | No | product | PLS UDE Debugger |  |  | Product Performance | Write all time (Overall ) | Time taken to write back to the memory (mS) | Product | milli-seconds | Continuous | Lower the better | Recommended value from KPIT Autosar practice 50 to 100ms. Can be measured by using a 1mS timer or by toggling a pin before write all function and after write all completion. Timing Architect tool can be used to measure as well
QUALITY | Milestone Delivery | Yes | release |  | Unipro |  | Review Effectiveness | Review coverage | Number of Configurable items released with review/ Total Configurable items eligible for review | Product | % | Ratio | Higher the better
QUALITY | Milestone Delivery | Yes | release |  | Unipro |  | Review Effectiveness | Review Effectiveness - SRS | Review Defects In SRS /(Discontinuities Escaped+Screen Discontinuities Found+Review Defects) * 100 | Process (Phase) | % | Ratio | Larger the Better | No. of Review Defects = 5 No. of Screen Defects = 4 No. of Discontinuities Escaped from Phase = 3 Review Effectiveness - Phase = 5/(5+4+3) * 100 = 40%
QUALITY | Milestone Delivery | Yes | release |  | Unipro |  | Review Effectiveness | Review Effectiveness - Project | Review Defects In Project /(Discontinuities Escaped+Screen Discontinuities Found+Review Defects) * 100 | Process (Project) | % | Ratio | Larger the Better | No. of Review Defects = 5 No. of Screen Defects = 4 No. of Discontinuities Escaped from Project = 3 Review Effectiveness - Project = 5/(5+4+3) * 100 = 40%
QUALITY | Milestone Delivery | No | V&V |  |  |  | Test Coverage | Requirements Test Coverage (Software / Integration Test) | (No. of Requirements Implemented in Test Cases / Total No. of Requirements) * 100 | Process (Project) | % | Ratio | Larger the Better
QUALITY | Milestone Delivery | No | V&V |  |  |  | Test Coverage | Test Automation coverage | Number of Test cases automated/ number of total test cases | Product | % | Ratio | Higher the better
QUALITY | Milestone Delivery | No | V&V |  |  |  | Test Execution | Negative Test Cases% | Number of Test Case Objectives/scenarios Marked as Negative Scenarios/ Total Test Cases | Product | Number | Ratio | NA
QUALITY | Milestone Delivery | No | V&V |  |  |  | Test Execution | Positive Test Cases% | Number of Test Case objectives/scenarios Marked as Positive Scenarios/ Total Test Cases | Product | Number | Ratio | NA
QUALITY | Milestone Delivery | No | V&V |  |  |  | Test Execution | Reliability Index ( For Test Automation ) | 1 - (Number of Failed Executions/Total Number Execution Attempts) | Product | Number | Continuous | Larger the Better | NA
QUALITY | Milestone Delivery | Yes | V&V |  |  | V&V | Test Execution | Test Pass Rate | Number of test cases passed/ Total number of test cases Testable | Product | % | Ratio | Higher the better
QUALITY | Milestone Delivery | Yes | release |  |  |  | Zero Defect Delivery | ZDD% based on External RE | 100 - (Rework Effort to fix findings from Customer / Total Effort x 100) | Process (Project) | % | Ratio | Larger the Better
QUALITY | Milestone Delivery | Yes | product | PLS UDE Debugger |  | V&V | Product Performance | Stack Usage (Algorithm need to write to be measured in XCP) | From OS algorithm | Product | % | Ratio | Lower the better
QUALITY | Milestone Delivery | Yes | product | PLS UDE Debugger |  |  | Product Performance | Overhead measurement Inter core communication, | IOs Will be checked | Product
QUALITY | Milestone Delivery | Yes | product | PLS UDE Debugger |  |  | Product Performance | Overhead measurement OS Scheduler | (Execution Time of timer ISR) | Product
QUALITY | Milestone Delivery | No | product | PLS UDE Debugger |  |  | Product Performance | Overhead measurement Critical sections |  | Product
QUALITY | Milestone Delivery | Yes | product | XCP tool CANAPE/ INCA |  | V&V | Product Performance | Calibration data upload time |  | Product
QUALITY | Milestone Delivery | Yes | release |  | Unipro |  | Review Effectiveness | Review Effectiveness - LLD | Review Defects In LLD /(Discontinuities Escaped+Screen Discontinuities Found+Review Defects) * 100 | % | Ratio | Larger the Better | No. of Review Defects = 5 No. of Screen Defects = 4 No. of Discontinuities Escaped from Phase = 3 Review Effectiveness - Phase = 5/(5+4+3) * 100 = 40%
QUALITY | Milestone Delivery | Yes | release |  | Unipro |  | Review Effectiveness | Review Effectiveness - Code | Review Defects In Code /(Discontinuities Escaped+Screen Discontinuities Found+Review Defects) * 100 | Ratio | Larger the Better | No. of Review Defects = 5 No. of Screen Defects = 4 No. of Discontinuities Escaped from Phase = 3 Review Effectiveness - Phase = 5/(5+4+3) * 100 = 40%
QUALITY | Milestone Delivery | Yes | release |  | Unipro |  | Review Effectiveness | Review Effectiveness - Test Case | Review Defects In Test case /(Discontinuities Escaped+Screen Discontinuities Found+Review Defects) * 100 | Larger the Better | No. of Review Defects = 5 No. of Screen Defects = 4 No. of Discontinuities Escaped from Phase = 3 Review Effectiveness - Phase = 5/(5+4+3) * 100 = 40%